## Hoja1
# | General Risk Description | Severity (1-5) | Probability (1-5) | Risk Level (S×P) |  | 1. Requirements & Planning
1 | System downtime impacting availability | 4 | 3 | 12 | Medium
2 | Data loss or corruption affecting reservations | 5 | 2 | 10 | Medium | # | General Risk Description | Severity (1-5) | Probability (1-5) | Risk Level (S×P)
3 | Unauthorized access leading to security breaches | 5 | 4 | 20 | High | 13 | Compliance violations with data protection laws | 5 | 3 | 15 (High)
4 | Cybersecurity threats (SQL injection, XSS, phishing, etc.) | 5 | 3 | 15 | High | 19 | Legal issues from unauthorized or incorrect reservation handling | 5 | 2 | 10 (Medium)
5 | Communication failures (email, notifications, API dependencies) | 3 | 4 | 12 | Medium | 20 | Inadequate training for system users and administrators | 3 | 3 | 9 (Medium)
6 | Network connectivity issues disrupting system use | 4 | 3 | 12 | Medium | 25 | Lack of accessibility features limiting usability for all users | 3 | 3 | 9 (Medium)
7 | System performance degradation during peak usage | 4 | 3 | 12 | Medium | 38 | Poorly written error messages causing user frustration | 3 | 3 | 9 (Medium)
8 | Authentication and access control vulnerabilities | 5 | 3 | 15 | High | 45 | Unclear or inconsistent reservation policies | 3 | 3 | 9 (Medium)
9 | Inconsistent or incorrect reservation data | 4 | 3 | 12 | Medium | 48 | Limited support for multi-language users | 2 | 3 | 6 (Low)
10 | Poor user experience leading to confusion and errors | 2 | 3 | 6 | Low
11 | Insufficient logging and monitoring for troubleshooting | 4 | 3 | 12 | Medium
12 | Lack of scalability as system usage grows | 4 | 3 | 12 | Medium | 2. Design
13 | Compliance violations with data protection laws | 5 | 3 | 15 | High
14 | Failure to implement multi-factor authentication | 5 | 3 | 15 | High | # | General Risk Description | Severity (1-5) | Probability (1-5) | Risk Level (S×P)
15 | Data exposure due to weak encryption or storage practices | 5 | 3 | 15 | High | 14 | Failure to implement multi-factor authentication | 5 | 3 | 15 (High)
16 | Manual reservation system conflicts with automated bookings | 4 | 2 | 8 | Medium | 32 | Hardcoded credentials or poor password policies | 4 | 4 | 16 (High)
17 | Poor system administration practices leading to misconfigurations | 4 | 3 | 12 | Medium | 44 | Poor firewall and network security configurations | 5 | 3 | 15 (High)
18 | Insufficient disaster recovery and backup strategies | 5 | 2 | 10 | Medium | 41 | Dependency on outdated or unsupported third-party libraries | 4 | 3 | 12 (Medium)
19 | Legal issues from unauthorized or incorrect reservation handling | 5 | 2 | 10 | Medium | 37 | Inconsistent UI across devices leading to usability issues | 3 | 3 | 9 (Medium)
20 | Inadequate training for system users and administrators | 3 | 3 | 9 | Medium | 36 | Lack of automation in system maintenance and testing | 4 | 3 | 12 (Medium)
21 | Poor session management increasing risk of unauthorized access | 4 | 3 | 12 | Medium | 39 | Inability to track and audit system modifications | 4 | 3 | 12 (Medium)
22 | Overuse of system resources causing high operational costs | 3 | 2 | 6 | Low
23 | Ineffective role-based access control enforcement | 5 | 3 | 15 | High
24 | API and third-party service failures impacting functionality | 3 | 3 | 9 | Medium | 3. Development
25 | Lack of accessibility features limiting usability for all users | 3 | 3 | 9 | Medium
26 | Incorrect handling of time zones affecting scheduling | 3 | 1 | 3 | Low | # | General Risk Description | Severity (1-5) | Probability (1-5) | Risk Level (S×P)
27 | System misuse by unauthorized or unintended users | 3 | 3 | 9 | Medium | 4 | Cybersecurity threats (SQL injection, XSS, phishing, etc.) | 5 | 3 | 15 (High)
28 | Failure to handle user support and complaints efficiently | 3 | 3 | 9 | Medium | 8 | Authentication and access control vulnerabilities | 5 | 3 | 15 (High)
29 | Data inconsistencies between different user sessions | 3 | 2 | 6 | Low | 23 | Ineffective role-based access control enforcement | 5 | 3 | 15 (High)
30 | Miscommunication between stakeholders affecting system updates | 3 | 3 | 9 | Medium | 40 | Failure to implement rate-limiting against brute-force attacks | 5 | 3 | 15 (High)
31 | Outdated software components leading to security vulnerabilities | 4 | 2 | 8 | Medium | 34 | Unauthorized modification of reservation data | 5 | 3 | 15 (High)
32 | Hardcoded credentials or poor password policies | 4 | 4 | 16 | High | 21 | Poor session management increasing risk of unauthorized access | 4 | 3 | 12 (Medium)
33 | Failure to update system software and security patches | 5 | 3 | 15 | High | 12 | Lack of scalability as system usage grows | 4 | 3 | 12 (Medium)
34 | Unauthorized modification of reservation data | 5 | 3 | 15 | High | 17 | Poor system administration practices leading to misconfigurations | 4 | 3 | 12 (Medium)
35 | Delays in system updates and feature enhancements | 4 | 3 | 12 | Medium | 11 | Insufficient logging and monitoring for troubleshooting | 4 | 3 | 12 (Medium)
36 | Lack of automation in system maintenance and testing | 4 | 3 | 12 | Medium
37 | Inconsistent UI across devices leading to usability issues | 3 | 3 | 9 | Medium
38 | Poorly written error messages causing user frustration | 3 | 3 | 9 | Medium | 4. Testing
39 | Inability to track and audit system modifications | 4 | 3 | 12 | Medium
40 | Failure to implement rate-limiting against brute-force attacks | 5 | 3 | 15 | High | # | General Risk Description | Severity (1-5) | Probability (1-5) | Risk Level (S×P)
41 | Dependency on outdated or unsupported third-party libraries | 4 | 3 | 12 | Medium | 18 | Insufficient disaster recovery and backup strategies | 5 | 2 | 10 (Medium)
42 | Hard-to-read or missing documentation affecting user adoption | 3 | 3 | 9 | Medium | 33 | Failure to update system software and security patches | 5 | 3 | 15 (High)
43 | Insufficient stress testing leading to crashes under high loads | 4 | 3 | 12 | Medium | 31 | Outdated software components leading to security vulnerabilities | 4 | 2 | 8 (Medium)
44 | Poor firewall and network security configurations | 5 | 3 | 15 | High | 43 | Insufficient stress testing leading to crashes under high loads | 4 | 3 | 12 (Medium)
45 | Unclear or inconsistent reservation policies | 3 | 3 | 9 | Medium | 50 | Lack of regular database maintenance leading to performance issues | 5 | 3 | 15 (High)
46 | Users not receiving confirmation emails or notifications | 3 | 3 | 9 | Medium
47 | Lack of system feedback causing repeated user actions | 3 | 3 | 9 | Medium
48 | Limited support for multi-language users | 2 | 3 | 6 | Low | 5. Deployment & Maintenance
49 | Inadequate server load balancing leading to system slowdowns | 4 | 3 | 12 | Medium
50 | Lack of regular database maintenance leading to performance issues | 5 | 3 | 15 | High | # | General Risk Description | Severity (1-5) | Probability (1-5) | Risk Level (S×P)
51 | Database deadlocks causing delays or failures in transactions | 4 | 3 | 12 | Medium | 1 | System downtime impacting availability | 4 | 3 | 12 (Medium)
52 | Poorly optimized database queries slowing down the system | 4 | 4 | 16 | High | 2 | Data loss or corruption affecting reservations | 5 | 2 | 10 (Medium)
53 | Lack of database indexing causing inefficient searches | 4 | 3 | 12 | Medium | 6 | Network connectivity issues disrupting system use | 4 | 3 | 12 (Medium)
[6 empty] | 7 | System performance degradation during peak usage | 4 | 3 | 12 (Medium)
[6 empty] | 24 | API and third-party service failures impacting functionality | 3 | 3 | 9 (Medium)
[6 empty] | 30 | Miscommunication between stakeholders affecting system updates | 3 | 3 | 9 (Medium)
[6 empty] | 29 | Data inconsistencies between different user sessions | 3 | 2 | 6 (Low)
[6 empty] | 46 | Users not receiving confirmation emails or notifications | 3 | 3 | 9 (Medium)
[6 empty] | 47 | Lack of system feedback causing repeated user actions | 3 | 3 | 9 (Medium)
[6 empty] | 52 | Poorly optimized database queries slowing down the system | 4 | 4 | 16 (High)
[6 empty] | 53 | Lack of database indexing causing inefficient searches | 4 | 3 | 12 (Medium)
[6 empty] | 51 | Database deadlocks causing delays or failures in transactions | 4 | 3 | 12 (Medium)
[6 empty] | 49 | Inadequate server load balancing leading to system slowdowns | 4 | 3 | 12 (Medium)