## Master Project Schedule
MASTER PROJECT SCHEDULE TEMPLATE
| PROJECT TITLE |  | START DATE
| Reservación de aulas (Apart-me) |  | 2025-02-20 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
|  |  | 2025-05-09 |  |  | 79
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | Planeación | In Progress |  | 2025-02-20 | 2025-03-04 | 13 |  | Not Started
1.1 | Lectura de requisitos | Complete | Todo el equipo | 2025-02-21 | 2025-02-22 | 2 |  | In Progress
1.4 | Definición de alcance y objetivos | Complete |  | 2025-02-22 | 2025-02-23 | 2 |  | Complete
1.5 | Identificaión de requerimientos | Complete |  | 2025-02-24 | 2025-02-26 | 3 |  | On Hold
1.6 | Separacionde requerimientos | Complete |  | 2025-02-26 | 2025-02-27 | 2
1.7 | Analisis de riesgos | Not Started |  | 2025-03-03 | 2025-03-04 | 2
2 | Analisis | In Progress |  | 2025-03-05 | 2025-03-12 | 8
2.1 | Requisitos funcionales, no funcionales y tecnologicos | In Progress |  | 2025-03-05 | 2025-03-06 | 2
2.2 | Asignación de tecnologias | Not Started |  | 2025-03-06 | 2025-03-07 | 2
2.3 | Asignaciones de herramientas | Not Started |  | 2025-03-07 | 2025-03-08 | 2
2.4 | Asignaciones de tareas | Not Started |  | 2025-03-09 | 2025-03-12 | 4
3 | Diseño | Not Started |  | 2025-03-13 | 2025-03-20 | 8
3.1 | Diagrama fisico de la base de datos | Not Started |  | 2025-03-13 | 2025-03-14 | 2
3.2 | Diagrama casos de uso | Not Started |  | 2025-03-15 | 2025-03-17 | 3
3.2.1 | Diagrama componentes | Not Started |  | 2025-03-17 | 2025-03-18 | 2
3.2.2 | Diseño UL/UX | Not Started |  | 2025-03-18 | 2025-03-20 | 3
4 | Desarrollo | Not Started |  | 2025-03-21 | 2025-04-06 | 17 |  | 5 | Testing | Not Started | 2025-04-07 | 2025-04-18 | 12
4.1 | Creacion de base de datos | Not Started |  | 2025-03-21 | 2025-03-25 | 5 |  | 5.1 | Verificar inicios de sesion | Not Started | 2025-04-07 | 2025-04-09 | 3
4.2 | Desarrollo de codigo conectado a base de datos | Not Started |  | 2025-03-25 | 2025-03-28 | 4 |  | 5.2 | Verificar registros de usuario | Not Started | 2025-04-09 | 2025-04-11 | 3
4.3 | Desarrollo de frontend | Not Started |  | 2025-03-28 | 2025-04-01 | 5 |  | 5.3 | Conectividad al servidor | Not Started | 2025-04-11 | 2025-04-14 | 4
4.4 | Ajustar medidas de seguridad(https) | Not Started |  | 2025-04-01 | 2025-04-04 | 4 |  | 5.4 | Verificacion de apartado | Not Started | 2025-04-14 | 2025-04-18 | 5
4.5 | Generacion de log para llevar historial | Not Started |  | 2025-04-04 | 2025-04-06 | 3

## BLANK - Master Project Schedule
MASTER PROJECT SCHEDULE
| PROJECT TITLE |  | START DATE
PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
1
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION |  |  |  |  | 1 |  | Not Started
1.1 | – Project Charter | Not Started |  |  |  | 1 |  | In Progress
1.1.1 | –– Project Charter Revisions | Not Started |  |  |  | 1 |  | Complete
1.2 | – Research | Not Started |  |  |  | 1 |  | On Hold
1.3 | – Projections | Not Started |  |  |  | 1
1.4 | – Stakeholders | Not Started |  |  |  | 1
1.5 | – Guidelines | Not Started |  |  |  | 1
1.6 | – Project Initiation | Not Started |  |  |  | 1
2 | PROJECT DEFINITION AND PLANNING |  |  |  |  | 1
2.1 | – Scope & Goal Setting | Not Started |  |  |  | 1
2.2 | – Budget | Not Started |  |  |  | 1
2.3 | – Communication Plan | Not Started |  |  |  | 1
2.4 | – Risk Management | Not Started |  |  |  | 1
3 | PROJECT LAUNCH & EXECUTION |  |  |  |  | 1
3.1 | – Status & Tracking | Not Started |  |  |  | 1
3.2 | – KPIs | Not Started |  |  |  | 1
3.2.1 | –– Monitoring | Not Started |  |  |  | 1
3.2.2 | –– Forecasts | Not Started |  |  |  | 1
3.3 | – Project Updates | Not Started |  |  |  | 1
3.3.1 | –– Chart Updates | Not Started |  |  |  | 1
4 | PROJECT PERFORMANCE / MONITORING |  |  |  |  | 1
4.1 | – Project Objectives | Not Started |  |  |  | 1
4.2 | – Quality Deliverables | Not Started |  |  |  | 1
4.3 | – Effort & Cost Tracking | Not Started |  |  |  | 1
4.4 | – Project Performance | Not Started |  |  |  | 1

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.